## Project Plan
Project Title
|  |  | Start Week | 2018-01-26
Week | Tasks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Ending |  | 2018-01-26 | 2018-02-02 | 2018-02-09 | 2018-02-16 | 2018-02-23 | 2018-03-02 | 2018-03-09 | 2018-03-16 | 2018-03-23 | 2018-03-30
|  | 2018-01-26 | 2018-02-02 | 2018-02-09 | 2018-02-16 | 2018-02-23 | 2018-03-02 | 2018-03-09 | 2018-03-16 | 2018-03-23 | 2018-03-30
Phase A - Requirements | Requirements gathering | bar: 2018-01-26
Identifying Use Cases | bar: 2018-02-02
Modeling mock-ups | bar: 2018-02-02
Milestone 1 - Phase A completed
Phase B - Design | Class Diagram | bar: 2018-02-02
State Diagram | bar: 2018-02-02
Sequence Diagram | bar: 2018-02-09
Activity Diagram | bar: 2018-02-09
Milestone 2 - Phase B completed
Phase C - Implementation | System Login | bar: 2018-02-16
Loading data from github | bar: 2018-02-23
Unit Testing | bar: 2018-02-23
Milestone 3 - Authentication & Data Import completed
Implement algorithm for checking plagiarism | bar: 2018-03-02
Generating and Viewing Plagiarism reports | bar: 2018-03-09
Unit Testing | bar: 2018-03-09
Milestone 4 - Plagiarism Detection & Report Generation completed
Downloading plagiarism reports | bar: 2018-03-16
Escalate cases to authorities | bar: 2018-03-16
Unit Testing | bar: 2018-03-16
Milestone 5 - Downloading Reports & Escalation completed
Integration Testing | bar: 2018-03-23
Milestone 6 - Integration Testing completed
Acceptance Testing | bar: 2018-03-30
Deployment & Maintainence | bar: 2018-03-30
Milestone 7 - Acceptance Testing completed
Denotes an ongoing task
Denotes the completion of a task